## 1. Executive Dashboard
⚡ HARYANA LOAD FORECAST — ACCURACY STRATEGY DASHBOARD
Diagnostic Analysis ¦ Root-Cause Identification ¦ Precision Roadmap to ≥98% Daily Accuracy
CURRENT STATE vs TARGET
T+1 CURRENT |  |  |  | T+2 CURRENT | TARGET
95.0% |  |  |  | 92.2% | ≥ 98.0%
27-day average |  |  |  | 27-day average | Both T+1 & T+2
GAP ANALYSIS: HOW FAR FROM TARGET
Metric | Current | Target | Gap | Status
T+1 Daily Accuracy | 95.0% | 98.0% | -3.0pp | 🔴 NEEDS FIX
T+2 Daily Accuracy | 92.2% | 98.0% | -5.8pp | 🔴 CRITICAL
T+1 Block MAPE | 4.66% | <2.0% | 2.66pp excess | 🟠 HIGH
T+2 Block MAPE | 7.72% | <2.0% | 5.72pp excess | 🔴 CRITICAL
Days T+1 ≥98% | 0 / 27 | 25+ / 27 | -27 days | 🔴 ZERO DAYS MET
T+1 Best Day | 97.5% (Apr-24) | 98.0% | -0.5pp | 📊 Close on best days
ROOT CAUSES RANKED BY IMPACT (from block-level data analysis)
# | Root Cause | Evidence | MAPE Impact | Fix In
1 | Afternoon ramp 13-18h under-forecast | T+1 MAPE 7.0%, bias -68 MW avg blocks 53-72 | HIGH | 2-3 wks
2 | T+2 night block systematic overforecast | Night T+2 bias = -281 MW, MAPE 5.7% | HIGH | 1 wk
3 | Blocks 60-65 (15:00-16:15) worst zone | T+1 8.1% MAPE, T+2 12.4% — entire Haryana peak window | HIGH | 2-3 wks
4 | No block-level bias correction table | +30 MW T+1 mean bias, +/-559 MW std: no systematic removal | HIGH | 1 wk
5 | Weather not capturing convective heat | April apparent_temp >40C not mapped to load gain | MED | 3 wks
6 | Weekend/holiday profile missing | 89-91% on 5 weekend days in April | MED | 2-3 wks
7 | T+2 decay too steep, night blocks uncorrected | T+2 error std 756 MW vs T+1 559 MW | MED | 1-2 wks
8 | Similar-day pool too shallow (7-14 days) | Mismatch on hot days with no recent analogues | LOW-MED | 3 wks

## 2. Block MAPE Analysis
96-BLOCK MAPE ANALYSIS — WHERE IS ACCURACY BEING LOST?
Block | Time | T+1 MAPE% | T+2 MAPE% | T+1 Bias MW | T+2 Bias MW | Risk Zone
1 | 00:00 | 1.11 | 6.72 | -93 | -328 | 🟢 Good
2 | 00:15 | 1.21 | 6.81 | -85 | -313 | 🟢 Good
3 | 00:30 | 1.04 | 6.66 | -80 | -321 | 🟢 Good
4 | 00:45 | 1.23 | 6.73 | -95 | -349 | 🟢 Good
5 | 01:00 | 1.3 | 6.92 | -101 | -338 | 🟢 Good
6 | 01:15 | 1.49 | 6.9 | -110 | -326 | 🟢 Good
7 | 01:30 | 1.27 | 7.09 | -108 | -331 | 🟢 Good
8 | 01:45 | 0.91 | 7 | -71 | -314 | 🟢 Good
9 | 02:00 | 0.95 | 6.94 | -64 | -297 | 🟢 Good
10 | 02:15 | 1.15 | 6.44 | -76 | -349 | 🟢 Good
11 | 02:30 | 1.08 | 6.47 | -54 | -374 | 🟢 Good
12 | 02:45 | 1.12 | 6.33 | -65 | -390 | 🟢 Good
13 | 03:00 | 0.96 | 6.36 | -50 | -444 | 🟢 Good
14 | 03:15 | 0.8 | 6.51 | -39 | -445 | 🟢 Good
15 | 03:30 | 0.8 | 6.6 | -37 | -436 | 🟢 Good
16 | 03:45 | 0.72 | 6.5 | -31 | -433 | 🟢 Good
17 | 04:00 | 0.76 | 6.63 | -39 | -424 | 🟢 Good
18 | 04:15 | 0.81 | 6.91 | -30 | -446 | 🟢 Good
19 | 04:30 | 0.92 | 6.88 | -4 | -441 | 🟢 Good
20 | 04:45 | 1.11 | 6.63 | -13 | -457 | 🟢 Good
21 | 05:00 | 1.1 | 5.52 | -13 | -415 | 🟢 Good
22 | 05:15 | 1.41 | 4.44 | 20 | -350 | 🟢 Good
23 | 05:30 | 1.42 | 3.84 | 17 | -307 | 🟢 Good
24 | 05:45 | 1.61 | 3.54 | 45 | -231 | 🟢 Good
25 | 06:00 | 1.76 | 3.41 | 66 | -116 | 🟢 Good
26 | 06:15 | 2.11 | 3.61 | 61 | -66 | 🟢 Good
27 | 06:30 | 2.1 | 3.33 | 78 | 13 | 🟢 Good
28 | 06:45 | 3.17 | 2.95 | 142 | 29 | 🟡 Medium
29 | 07:00 | 3.01 | 4.16 | 162 | 42 | 🟡 Medium
30 | 07:15 | 2.89 | 4.06 | 151 | 32 | 🟢 Good
31 | 07:30 | 2.84 | 3.9 | 138 | -24 | 🟢 Good
32 | 07:45 | 2.98 | 4.18 | 142 | -29 | 🟢 Good
33 | 08:00 | 3.32 | 5.43 | 174 | 11 | 🟡 Medium
34 | 08:15 | 3.39 | 5.45 | 177 | 12 | 🟡 Medium
35 | 08:30 | 3.24 | 5.57 | 141 | -6 | 🟡 Medium
36 | 08:45 | 3.36 | 5.71 | 123 | -14 | 🟡 Medium
37 | 09:00 | 4.08 | 6.25 | 112 | 9 | 🟡 Medium
38 | 09:15 | 4.48 | 6.71 | 88 | -7 | 🟡 Medium
39 | 09:30 | 5.08 | 7.39 | 82 | -7 | 🟠 High
40 | 09:45 | 5.19 | 7.53 | 102 | 4 | 🟠 High
41 | 10:00 | 5.08 | 7.8 | 107 | 15 | 🟠 High
42 | 10:15 | 5.58 | 8.1 | 137 | 48 | 🟠 High
43 | 10:30 | 5.6 | 8.34 | 124 | 52 | 🟠 High
44 | 10:45 | 5.76 | 8.4 | 114 | 43 | 🟠 High
45 | 11:00 | 5.72 | 8.57 | 107 | 25 | 🟠 High
46 | 11:15 | 5.83 | 9.16 | 73 | -20 | 🟠 High
47 | 11:30 | 5.95 | 10.02 | 44 | -40 | 🟠 High
48 | 11:45 | 6.11 | 10.44 | 33 | -51 | 🟠 High
49 | 12:00 | 5.82 | 10.92 | -9 | -107 | 🟠 High
50 | 12:15 | 5.81 | 11.35 | -31 | -138 | 🟠 High
51 | 12:30 | 5.76 | 11.14 | -42 | -160 | 🟠 High
52 | 12:45 | 5.7 | 10.74 | -63 | -175 | 🟠 High
53 | 13:00 | 5.86 | 11.12 | -58 | -180 | 🟠 High
54 | 13:15 | 6.09 | 11.35 | -82 | -219 | 🟠 High
55 | 13:30 | 6.55 | 11.48 | -126 | -260 | 🟠 High
56 | 13:45 | 6.84 | 11.41 | -133 | -264 | 🟠 High
57 | 14:00 | 6.61 | 10.73 | -137 | -278 | 🟠 High
58 | 14:15 | 6.96 | 10.9 | -151 | -280 | 🟠 High
59 | 14:30 | 7.2 | 11.02 | -148 | -284 | 🔴 Critical
60 | 14:45 | 7.57 | 11.84 | -183 | -314 | 🔴 Critical
61 | 15:00 | 8.13 | 12.35 | -159 | -295 | 🔴 Critical
62 | 15:15 | 8.01 | 12.18 | -146 | -273 | 🔴 Critical
63 | 15:30 | 7.86 | 12.12 | -143 | -261 | 🔴 Critical
64 | 15:45 | 7.88 | 11.66 | -112 | -218 | 🔴 Critical
65 | 16:00 | 7.73 | 11.09 | -75 | -172 | 🔴 Critical
66 | 16:15 | 7.19 | 10.65 | -61 | -137 | 🔴 Critical
67 | 16:30 | 6.98 | 9.88 | -17 | -79 | 🟠 High
68 | 16:45 | 6.96 | 9.46 | 5 | -40 | 🟠 High
69 | 17:00 | 6.76 | 8.65 | 45 | 9 | 🟠 High
70 | 17:15 | 6.29 | 8.33 | 79 | 49 | 🟠 High
71 | 17:30 | 6.06 | 8.48 | 113 | 85 | 🟠 High
72 | 17:45 | 6.53 | 8.83 | 135 | 143 | 🟠 High
73 | 18:00 | 5.96 | 7.22 | 193 | 211 | 🟠 High
74 | 18:15 | 6.15 | 7.34 | 289 | 290 | 🟠 High
75 | 18:30 | 6.42 | 7.56 | 333 | 342 | 🟠 High
76 | 18:45 | 6 | 6.92 | 360 | 332 | 🟠 High
77 | 19:00 | 5.39 | 5.62 | 379 | 347 | 🟠 High
78 | 19:15 | 5.22 | 5.33 | 340 | 288 | 🟠 High
79 | 19:30 | 4.95 | 5.18 | 283 | 207 | 🟡 Medium
80 | 19:45 | 5.15 | 5.51 | 276 | 156 | 🟠 High
81 | 20:00 | 5.8 | 6.39 | 320 | 139 | 🟠 High
82 | 20:15 | 6.58 | 7.32 | 309 | 98 | 🟠 High
83 | 20:30 | 7.96 | 8.89 | 334 | 109 | 🔴 Critical
84 | 20:45 | 7.96 | 8.84 | 279 | 58 | 🔴 Critical
85 | 21:00 | 7.74 | 8.69 | 212 | -23 | 🔴 Critical
86 | 21:15 | 6.95 | 8.13 | 174 | -96 | 🟠 High
87 | 21:30 | 6.61 | 7.61 | 110 | -167 | 🟠 High
88 | 21:45 | 6.71 | 7.83 | 98 | -201 | 🟠 High
89 | 22:00 | 7.02 | 7.88 | 4 | -290 | 🔴 Critical
90 | 22:15 | 7.32 | 8.33 | -64 | -336 | 🔴 Critical
91 | 22:30 | 7.33 | 9 | -201 | -464 | 🔴 Critical
92 | 22:45 | 7.36 | 8.86 | -226 | -487 | 🔴 Critical
93 | 23:00 | 7.45 | 8.65 | -224 | -494 | 🔴 Critical
94 | 23:15 | 6.86 | 8.38 | -227 | -507 | 🟠 High
95 | 23:30 | 7.26 | 8.03 | -240 | -512 | 🔴 Critical
96 | 23:45 | 7.33 | 7.89 | -228 | -496 | 🔴 Critical
KEY FINDINGS FROM BLOCK ANALYSIS
🔴 Blocks 60-65 (15:00-16:15) = WORST in entire day: T+1 MAPE 7.9-8.1%, T+2 MAPE 11-12%
🔴 Afternoon zone 52-68 (13:00-17:00) = sustained high error, AC ramp not being captured
🟠 Evening 73-96 (18:15-00:00) = T+1 manageable 6.6% but T+2 systematic underforecast
🟠 Blocks 83-85 (20:30-21:15) = second error cluster, evening cooling turn-off behaviour
🟢 Night blocks 1-32 = BEST zone for T+1 (1.5% MAPE) but T+2 has -281 MW night bias
📌 Fix priority order: S1 Bias Table → S3 T+2 Night → S2 Afternoon Ramp → S4 Weekend Profile

## 3. Daily Accuracy Tracker
DAILY ACCURACY LOG — APRIL 2026 (HARYANA)
Date | Day Type | T+1 Acc% | T+2 Acc% | T+1 Gap to 98% | Rating | Action Needed
01-Apr-2026 | Weekday | 96.14 | 89 | 1.86 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
02-Apr-2026 | Weekday | 95.75 | 93.34 | 2.25 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
03-Apr-2026 | Weekday | 96.18 | 96.17 | 1.82 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
04-Apr-2026 | Weekend | 95.2 | 94.83 | 2.8 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
05-Apr-2026 | Weekend | 91.77 | 89 | 6.23 | 🔴 UNACCEPTABLE | Full audit: weather+calendar+bias correction
06-Apr-2026 | Weekday | 93.45 | 91 | 4.55 | 🟠 POOR | Check weather delta + calendar factor
07-Apr-2026 | Weekday | 89.2 | 93.8 | 8.8 | 🔴 UNACCEPTABLE | Full audit: weather+calendar+bias correction
08-Apr-2026 | Weekday | 95.8 | 88 | 2.2 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
09-Apr-2026 | Weekday | 95.7 | 88 | 2.3 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
10-Apr-2026 | Weekday | 94.5 | 91.5 | 3.5 | 🟠 POOR | Check weather delta + calendar factor
11-Apr-2026 | Weekend | 96.1 | 96.4 | 1.9 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
12-Apr-2026 | Weekend | 91.68 | 86.98 | 6.32 | 🔴 UNACCEPTABLE | Full audit: weather+calendar+bias correction
13-Apr-2026 | Weekday | 96.1 | 94.5 | 1.9 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
14-Apr-2026 | Weekday | 97.3 | 96.24 | 0.7 | 🟢 GOOD | Maintain — check weather features
15-Apr-2026 | Weekday | 97.44 | 94 | 0.56 | 🟢 GOOD | Maintain — check weather features
16-Apr-2026 | Weekday | 97.26 | 95.6 | 0.74 | 🟢 GOOD | Maintain — check weather features
17-Apr-2026 | Weekday | 93.86 | 92.73 | 4.14 | 🟠 POOR | Check weather delta + calendar factor
18-Apr-2026 | Weekend | 96.27 | 97.63 | 1.73 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
19-Apr-2026 | Weekend | 91.98 | 88.9 | 6.02 | 🔴 UNACCEPTABLE | Full audit: weather+calendar+bias correction
20-Apr-2026 | Weekday | 94.85 | 90.3 | 3.15 | 🟠 POOR | Check weather delta + calendar factor
21-Apr-2026 | Weekday | 96.22 | 88.58 | 1.78 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
22-Apr-2026 | Weekday | 96.36 | 90.26 | 1.64 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
23-Apr-2026 | Weekday | 96.38 | 94.36 | 1.62 | 🟡 ACCEPTABLE | Tune afternoon ramp + horizon calibration
24-Apr-2026 | Weekday | 97.45 | 94.47 | 0.55 | 🟢 GOOD | Maintain — check weather features
25-Apr-2026 | Weekend | 97.09 | 95.87 | 0.91 | 🟢 GOOD | Maintain — check weather features
26-Apr-2026 | Weekend | 94.85 | 91.7 | 3.15 | 🟠 POOR | Check weather delta + calendar factor
27-Apr-2026 | Weekday | 90.55 | 85.96 | 7.45 | 🔴 UNACCEPTABLE | Full audit: weather+calendar+bias correction
SUMMARY: T+1 mean=95.0% ¦ T+2 mean=92.2% ¦ Best T+1=97.5% ¦ Worst T+1=89.2% ¦ Days below 92%: 5

## 4. Fix Strategies
12-STRATEGY PRECISION IMPROVEMENT PLAN — TARGET ≥98% DAILY ACCURACY
Perspective: SLDC Grid Operator + 10-Year ML Forecasting Engineer ¦ Haryana 96-Block DAM Context
S# | Strategy / Fix | Target Metric | Acc Gain | Implementation Steps | Code Phase | Timeline | Priority
S1 | Block-Level Bias Correction Table Systematic offset removal per-block | T+1 MAPE <2% per block | +1.5-2.0pp | 1. Compute mean(forecast-actual) per time_block over rolling 30 days 2. Build bias_table[96] separately for weekday/weekend 3. Apply correction: forecast[b] -= bias_table[b] for future blocks 4. Smooth with uniform_filter1d(size=4) to avoid block-by-block noise 5. Rebuild every Monday; track correction drift weekly | Phase 18 (Live Error) Phase 22 (Horizon Cal) | 1 week | 🔴 P0
S2 | Afternoon Ramp Feature Engineering Dedicated 13:00-17:00 weather correction | Blocks 52-68 MAPE <4% | +0.8-1.2pp | 1. Add heat_index = f(temperature, humidity) as new feature 2. Split weather_weight[b] into 3 regimes: morning / afternoon / evening 3. Afternoon regime: temperature_weight x1.4, humidity_weight x1.2 4. Detect ramp-onset block from solar_radiation curve 5. Haryana April-June: apparent_temp >38C triggers ramp_boost factor | Phase 9 (Weather Delta) Phase 11 (Weather Impact) | 2-3 weeks | 🔴 P0
S3 | T+2 Night Block Dedicated Bias Fix Corrects -281 MW systematic night error | T+2 MAPE <5% night | +1.5-2.0pp T+2 | 1. Build bias_table_t2[96] from historical T+2 vs actual errors 2. Night blocks 1-32: apply median(t2_errors) as additive correction 3. Taper correction: 100% at block 1, linearly to 30% at block 48 4. Set correction=0 from block 49+ (daytime T+2 more stable) 5. Track drift weekly, rebuild monthly | Phase 28 (T+2 Forecast) New: t2_bias_correction.py | 1 week | 🔴 P0
S4 | Weekend/Holiday Load Profile Haryana-specific regime separation | Weekend T+1 >96% | +1.5-2.5pp wknds | 1. Create historical_baseline_weekend[96] from past 20 weekends 2. Load Haryana state holidays + national holidays into calendar 3. Weekends: load 8-12% lower in 09:00-18:00 window 4. Build holiday_profile[type][96] — Holi, Diwali, Eid have distinct shapes 5. Bridge day detection: working-Sat or post-holiday Mon = unique profile | Phase 6 (Season/DayType) Phase 7 (Historical Baseline) | 2-3 weeks | 🟠 P1
S5 | Convective Weather Regime Switching April-June Haryana afternoon heat/aandhi | Anomaly days >95% | +0.5-1.0pp hot days | 1. Add regime_flag: NORMAL / PRE_MONSOON_HOT / DUSTY_AANDHI / RAINY 2. PRE_MONSOON_HOT trigger: apparent_temp >42°C, humidity <30% 3. Hot days: afternoon load RISES 5-8% above baseline (AC surge) 4. Dusty/aandhi days: load DROPS 3-5% in 15:00-18:00 window 5. Reduce clamp tolerance on anomaly days to allow larger correction | Phase 10 (Anomaly Detection) Phase 11 (Weather Impact) | 2-3 weeks | 🟠 P1
S6 | Adaptive Baseline Window by Season 7-day window not optimal for all conditions | Baseline MAPE <3% | +0.5-0.8pp | 1. April-June: use 3-day baseline (fast daily ramp, recent days more relevant) 2. July-September: use 5-day baseline (monsoon variability) 3. October-March: use 7-day baseline (stable, longer history better) 4. Run best_baseline_window selection DAILY not weekly 5. Exclude days with >5% load anomaly from baseline pool | Phase 7 (Historical Baseline) | 2 weeks | 🟠 P1
S7 | Horizon Decay Rate Fix Current decay too aggressive for T+1 | Blocks 50-96 MAPE <5% | +0.5-0.8pp | 1. T+1: change decay 0.92 → 0.97 per block for stable afternoon 2. Split decay by zone: night=0.90 (stable), peak=0.97 (needs carry) 3. T+2: use separate decay=0.85 (limit bleed from day 1 correction) 4. Smooth live_ratio with EMA(3 blocks) instead of point estimate 5. Clamp live_ratio to [0.95,1.05] T+1, [0.92,1.08] T+2 | Phase 22 (Horizon Calibration) | 1 week | 🟠 P1
S8 | Spline Residual Shape Correction Replace flat error decay with shape carry | RMSE reduction >50 MW | +0.3-0.5pp | 1. Fit cubic spline to residual[b] across all known actual blocks 2. Extrapolate spline into future blocks (not flat seed_error extension) 3. Weight: 100% at boundary block, decay to 30% at block 96 4. Use scipy.interpolate.CubicSpline with extrapolation 5. Validate spline is monotone in overnight low-load zone | Phase 18 (Live Error) Phase 19 (Trend/Pattern) | 2 weeks | 🟠 P1
S9 | Dynamic Shrinkage Weights Block-level confidence replaces fixed weight | Shrinkage optimised per zone | +0.3-0.5pp | 1. Compute confidence[b] = 1 - rolling_mape_14d[b] for each block 2. MAPE <2% → shrink_weight 0.95 (trust forecast heavily) 3. MAPE >6% → shrink_weight 0.70 (pull hard toward baseline) 4. Recompute confidence weights every 7 days 5. Weather anomaly override: extreme days force shrink_weight=0.60 | Phase 21 (Forecast Shrinkage) | 1-2 weeks | 🟡 P2
S10 | Similar-Day Pool Expansion 365-day weighted search | Better analogues for hot/anomaly days | +0.3-0.5pp | 1. Expand similar-day search from 60 to 365-day rolling window 2. Use apparent_temperature proximity as primary weight factor 3. Weight recent matches 2x vs same-month last-year 4. Require minimum 5 similar days (not 3) for stable average 5. T+2: use similar-day load curve for synthetic T+1 (not raw lag-7) | Phase 8 (Similar Day Selection) | 2-3 weeks | 🟡 P2
S11 | Post-Pipeline Calibration Layer Isotonic regression per block-type | Final calibration all block types | +0.2-0.4pp | 1. Define 8 block-types: {night,morning-peak,afternoon,evening} x {weekday,weekend} 2. For each type: train isotonic regression on (forecast→actual) over 21-day window 3. Apply calibration after Phase 23 as final adjustment layer 4. Retrain calibrator every 7 days using sliding window 5. Apply only when forecast_confidence >0.80 to avoid over-correction | After Phase 23 (Final Clamp) New: calibration_layer.py | 3-4 weeks | 🟡 P2
S12 | SLDC Grid Operator Validator Sanity checks before schedule submission | Zero invalid SLDC outputs | Operational safety | 1. Ramp-rate check: ¦forecast[b] - forecast[b-1]¦ < 350 MW/15min 2. Floor check: forecast[b] >= 3500 MW (Haryana must-run minimum) 3. Ceiling check: forecast[b] <= 14000 MW (physical grid limit) 4. Energy balance: sum(forecast)*0.25 within ±3% of expected MU 5. Flag blocks >15% from baseline for manual review before submission | Phase 31 (SLDC Export) New: sldc_validator.py | 1 week | 🟠 P1

## 5. Implementation Roadmap
4-WEEK SPRINT ROADMAP — FROM 95% TO ≥98% ACCURACY
🚀 WEEK 1: Quick Wins — +2.0pp gain target
| Code | Strategy | Key Action | Acc Gain | Phase
| S1 | Block-Level Bias Correction | Build bias_table[96] weekday+weekend — 30-day median error per block | +1.5-2.0pp | Phase 18+22
| S3 | T+2 Night Block Fix | Add +250MW t2_bias_correction for blocks 1-32, taper to block 48 | +1.5pp T+2 | Phase 28
| S7 | Horizon Decay Fix | Change T+1 decay 0.92→0.97, add EMA smoothing to live_ratio | +0.5pp | Phase 22
| S12 | SLDC Validator | Ramp + floor + ceiling + energy balance sanity checks | Operational | Phase 31
⚙️ WEEK 2: Ramp & Baseline Fixes — +1.5pp gain target
| Code | Strategy | Key Action | Acc Gain | Phase
| S2 | Afternoon Ramp Feature | heat_index feature + split weather_weight 3 regimes | +1.0pp | Phase 9-11
| S6 | Adaptive Baseline Window | April→3-day, exclude anomaly days from pool | +0.6pp | Phase 7
| S8 | Spline Residual Shape | Replace flat seed_error decay with cubic spline extrapolation | +0.4pp | Phase 19
| S4 | Weekend Profile (Start) | baseline_weekend[96] + Haryana holiday calendar load | +1.0pp wknd | Phase 6-7
🎯 WEEK 3: Regime Tuning — +0.8pp gain target
| Code | Strategy | Key Action | Acc Gain | Phase
| S5 | Convective Regime Switch | PRE_MONSOON_HOT regime for apparent_temp >42°C | +0.8pp hot days | Phase 10
| S4 | Holiday Profiles (Complete) | Holi/Diwali/Eid/bridge-day profiles added | +0.5pp | Phase 6
| S9 | Dynamic Shrinkage | confidence[b] from 14-day rolling MAPE per block | +0.4pp | Phase 21
| S10 | Similar-Day Expand | 365-day pool + apparent_temp weighting for analogues | +0.3pp | Phase 8
✅ WEEK 4: Calibration & Hardening — Reach ≥98% target
| Code | Strategy | Key Action | Acc Gain | Phase
| S11 | Calibration Layer | Isotonic regression per block-type, retrain weekly | +0.3pp | New module
| - | Full Regression Test | Run all 19 available dates, compute MAPE delta per strategy | Validation | All phases
| - | SLDC QA Run | Validate 96-row outputs, energy balance, ramp rates | Operational | Phase 31
| - | Live Monitoring | Auto-alert when block MAPE >5% for 3 consecutive days | Monitoring | New module
PROJECTED ACCURACY IMPROVEMENT BY SPRINT END
| Sprint | T+1 Projected | T+2 Projected | Key Lever | Risk Level
| Baseline (Now) | 95.0% | 92.2% | No fixes applied | Current
| After Week 1 | 96.5-97.0% | 93.5-94.0% | Bias table + T+2 night fix | 🟡 Moderate
| After Week 2 | 97.0-97.5% | 94.5-95.5% | Afternoon ramp + adaptive baseline | 🟡 Moderate
| After Week 3 | 97.5-98.0% | 95.5-96.5% | Regime switch + weekend profiles | 🟢 Low
| After Week 4 | ≥98.0% | ≥96.5% | Calibration layer + full hardening | 🟢 Low

## 6. Code Templates
PRECISION FIX CODE TEMPLATES — Ready-to-integrate Python for VidyutPragya
S1 — Block-Level Bias Correction (bias_correction.py)
# Insert after Phase 18 in forecast pipeline
# Computes and applies per-block systematic bias correction
import numpy as np
from scipy.ndimage import uniform_filter1d
def compute_bias_table(historical_df, window_days=30, day_type="weekday"):
"""Compute per-block bias from recent errors. Returns bias_table[96] in MW."""
recent = historical_df.tail(window_days * 96)
if day_type == "weekday":
recent = recent[pd.to_datetime(recent["date"]).dt.dayofweek < 5]
elif day_type == "weekend":
recent = recent[pd.to_datetime(recent["date"]).dt.dayofweek >= 5]
bias_raw = recent.groupby("time_block").apply(
lambda g: np.percentile(g["forecast_t1"] - g["actual"], 50) # median bias
).values
return uniform_filter1d(bias_raw, size=4) # smooth to remove noise
def apply_bias_correction(forecast_96, bias_table, actual_blocks=0):
"""Apply bias correction to future blocks. Actual blocks unchanged."""
corrected = forecast_96.copy()
corrected[actual_blocks:] -= bias_table[actual_blocks:]
return np.maximum(corrected, 0)
# USAGE (Phase 22 region):
# bias_tbl = compute_bias_table(historical_df, window_days=30, day_type=day_type_flag)
# final_forecast = apply_bias_correction(final_forecast, bias_tbl, actual_blocks)
S2 — Afternoon Ramp Feature (afternoon_ramp.py)
# Insert into Phase 11 Weather Impact — Haryana April-June correction
def get_afternoon_ramp_weight(hour, season, apparent_temp_mean):
"""Returns weather weight multiplier for afternoon blocks."""
weight = 1.0
if season == "summer" and 13 <= hour <= 17:
heat_boost = min(1.6, 1.0 + (apparent_temp_mean - 38) * 0.04) if apparent_temp_mean > 38 else 1.0
ramp_factor = 1.0 + 0.3 * np.sin(np.pi * (hour - 13) / 4) # peak at 15h
weight = heat_boost * ramp_factor
elif season == "summer" and 10 <= hour <= 12:
weight = 1.15 # morning ramp-up
elif season == "monsoon" and 14 <= hour <= 17:
weight = 0.85 # cloud cover suppresses AC load
return weight
def compute_heat_index(temperature, humidity):
"""Steadman heat index for Indian conditions."""
return (-8.78 + 1.611*temperature + 2.338*humidity
- 0.146*temperature*humidity - 0.0123*temperature**2
- 0.0164*humidity**2 + 0.00221*temperature**2*humidity
+ 0.000725*temperature*humidity**2
- 0.00000358*temperature**2*humidity**2)
# In Phase 11 loop replace temperature_weight[b] with:
# temp_weight_adj = temperature_weight[b] * get_afternoon_ramp_weight(hour, season, app_temp_mean)
S3 — T+2 Night Block Bias Fix (t2_bias_fix.py)
# Insert into Phase 28 — corrects -281 MW systematic T+2 night error
def build_t2_bias_correction(t2_error_history):
"""Build per-block T+2 bias correction from historical T+2 errors.
t2_error_history: dict {block_1_to_96: list_of_error_values}
Returns correction_array[96] in MW (add to T+2 forecast)."""
correction = np.zeros(96)
for b in range(96):
errors = t2_error_history.get(b+1, [])
if len(errors) >= 7:
correction[b] = -np.percentile(errors, 50) # negate: we ADD to forecast
taper = np.ones(96)
taper[32:48] = np.linspace(1.0, 0.3, 16) # taper night correction out by mid-day
taper[48:] = 0.3
return correction * taper
def apply_t2_night_correction(t2_forecast_96, correction_array):
return np.maximum(t2_forecast_96 + correction_array, 0)
# USAGE in Phase 28 after T+2 pipeline runs:
# t2_corr = build_t2_bias_correction(t2_error_history_dict)
# t2_forecast_96 = apply_t2_night_correction(t2_forecast_96, t2_corr)
S12 — SLDC Grid Validator (sldc_validator.py)
# Grid operator safety layer before SLDC schedule submission
HARYANA_MUST_RUN = 3500 # MW minimum
HARYANA_MAX_RAMP = 350 # MW per 15-min block
HARYANA_PEAK_CAP = 14000 # MW physical limit
def validate_sldc_schedule(forecast_96, baseline_96, season="summer"):
"""Returns (validated_forecast, flags_list)."""
f = forecast_96.copy(); flags = []
floor = HARYANA_MUST_RUN * (0.9 if season == "winter" else 1.0)
low_b = np.where(f < floor)[0]
if len(low_b):
flags.append(f"FLOOR_BREACH: {len(low_b)} blocks below {floor:.0f} MW")
f[low_b] = floor
high_b = np.where(f > HARYANA_PEAK_CAP)[0]
if len(high_b):
flags.append(f"CEILING_BREACH: {len(high_b)} blocks above {HARYANA_PEAK_CAP} MW")
f[high_b] = HARYANA_PEAK_CAP
ramp_v = np.where(np.abs(np.diff(f)) > HARYANA_MAX_RAMP)[0]
if len(ramp_v):
flags.append(f"RAMP_BREACH: {len(ramp_v)} transitions exceed {HARYANA_MAX_RAMP} MW/15min")
dev_pct = np.abs(f - baseline_96) / np.maximum(baseline_96, 1) * 100
ext_b = np.where(dev_pct > 15)[0]
if len(ext_b):
flags.append(f"LARGE_DEVIATION: {len(ext_b)} blocks >15% from baseline — manual review")
e_gap = abs(f.sum()-baseline_96.sum())/baseline_96.sum()*100
if e_gap > 5:
flags.append(f"ENERGY_GAP: {e_gap:.1f}% vs baseline — check daily MU")
return f, flags